Supplementary Material S1

Applying Knowledge–Maturity Coevolution: a step-by-step guide with a worked example

This guide shows how to apply the method of the paper to a real development claim, from an organization's past records to the decision at each review. It uses the paper's notation and step numbers (Table 6, headroom procedure; Table 11, calibration protocol; Fig. 8, flowchart). Every number in the worked example was computed with the paper's code; the organization ("Org X"), its projects and records are fictional and serve only to illustrate the arithmetic.

What you need • An assessment log for one or more past programs (cost, activity class, K, M, shocks), or at least the outcome history of past integrated tests. • A review board that scores K and M for each claim at each review (Section 1). • A spreadsheet. The companion workbook KMC_Worksheet.xlsx implements Sections 3–5; the Python code (kmc_model.py) is needed only for the optional checks of Section 7.

| Step | What you do | Where in the paper | This guide |
| --- | --- | --- | --- |
| 0 | Define the claim, the target region, budget and exposure limit | Sec. III-C, Table 6 step 1 | Sec. 4.1 |
| 1 | Score K and M at every review; keep the log | Sec. III-H, IV-A; Tables 4, 11-1 | Sec. 1–2 |
| 2 | Calibrate the coefficients from records + public priors | Table 11, steps 2–4 | Sec. 3 |
| 3 | Compute the test threshold Ktest = max(Kneed, Khaz) | Eq. (17b), Table 6 steps 3/3b | Sec. 4.2 |
| 4 | At each review, choose the next activity | Table 6, steps 3–6; Fig. 8 | Sec. 4.3–4.5 |
| 5 | After the project, update the coefficients | Table 11, steps 5–6 | Sec. 5 |

# 1. Scoring K and M

Both quantities are scored per claim (for example, "combustion is stable across the operating envelope"), never averaged across subsystems.

## 1.1 Validated knowledge K

K = 1 − U / U0

U is the width of the validated prediction uncertainty for the intended-use quantity (for example, the area validation metric of the model against the most representative data, or the width of a credibility-weighted prediction interval), and U0 its value at the start of the program. If the initial model predicts the stability margin within ±40% and today's validated model within ±10%, then K = 1 − 10/40 = 0.75.

When no quantitative uncertainty is available yet, use the rubric of Table 4: score each K criterion 0–4, take the lowest mandatory criterion (never the average), and map 0, 1, 2, 3, 4 to K ≈ 0, 0.25, 0.5, 0.75, 1 as a first coding. Record the coding convention and keep it fixed within a program; the decision rule of Section 4 is insensitive to monotone recoding (paper, Sec. IV-D), but the calibrated coefficients are not.

## 1.2 Evidence-backed maturity M

M = Σv wv sv

List the test points v of the required demonstration envelope with weights wv that sum to one (by risk or by envelope area), and set sv = 1 where the acceptance criteria have been met under representative and repeatable conditions, 0 otherwise. Example: 20 equally weighted points, 8 passed: M = 0.40. Missing evidence is "not assessed", never zero.

## 1.3 Cost

Cumulative cost c is measured in one budget unit (BU) for the whole program, for example one integrated flight or one month of the test campaign. Only differences of c matter.

# 2. The assessment log

Record one line per review and per claim. Five columns are indispensable: cumulative cost, activity class performed since the last review (S simulation/analysis, E separate-effects test, T integrated test), K, M, and any shock (discrepancy) with its rework cost.

| Date | Project | Cum. cost (BU) | Activity | K | M | Event |
| --- | --- | --- | --- | --- | --- | --- |
| 2014-06 | Rocket R | 0.0 | — | 0.10 | 0.05 | baseline review |
| 2014-11 | Rocket R | 2.0 | T | 0.16 | 0.05 | flight 1 lost (shock) |
| 2019-03 | Engine E-1 | 1.0 | E | 0.37 | 0.12 | — |
| 2021-08 | CFD-2 | 3.0 | S | 0.57 | 0.30 | simulation plateau |

# 3. Calibrating the coefficients

The model has thirteen coefficients (paper, Eqs. (8)–(10) and Table 5). Calibrate first those that drive the plan most: the test hazard λT, the two ceilings and the main rates. Keep the paper's base values as priors for the others until records exist.

| Coefficient | Meaning | Record needed | Method |
| --- | --- | --- | --- |
| λT | integrated-test shock hazard per BU, × (1 − K)2 | outcomes of past integrated tests and K before each | likelihood + public prior (3.1) |
| eT | knowledge gained per BU of integrated testing | K before consecutive tests | least squares (3.2) |
| rS, rE, rT | main rates of S, E, T | K or M versus cost within a campaign | log-linear fit (3.3) |
| kb, kl; mb, ml | ceilings K̄(M) and M̄(K) | plateaus of S and T campaigns | linear regression (3.4) |
| eE, λE, δK, δM, ρ | secondary credit, small-test hazard, shock size, rework | — | paper base values |

## 3.1 Test hazard λT: likelihood and prior

For integrated test n with cost cf and assessed knowledge Kn, the probability of a discrepancy is

pn(λ) = 1 − exp[ −λ (1 − Kn)2 cf ]

and the likelihood of the observed history (failures F, successes S) is L(λ) = Πn∈F pn · Πn∈S (1 − pn). Maximize ln L over λ with a one-dimensional search (the workbook does it on a grid). Because a few tests give a wide estimate, combine L with a public prior, for example ln λ ~ Normal(ln 0.90, 0.52) from the FAA first-flight data of the paper (Sec. VI-B), and use the posterior median.

Worked example: Rocket R (8 launches, 2014–2024, first success on flight 8, cf = 2 BU) K before flights 1–8: 0.10, 0.16, 0.21, 0.27, 0.32, 0.37, 0.42, 0.47; outcomes: seven failures, then success. Data only: λ̂T = 2.55 per BU (flight 1: 1 − exp(−2.55 × 0.902 × 2) = 0.98). With the FAA prior: posterior median 1.48 per BU, 90% interval 0.80–2.68. Org X uses λT = 1.5.

Figure S1. Rocket R: failure probability per flight from the data alone (dashed) and from the posterior median (bars).

## 3.2 Knowledge per integrated test eT

With ΔKn the increase of K between consecutive tests and xn = (1 − Kn) cf, fit ΔKn = eT xn through the origin:

êT = Σ ΔKn xn / Σ xn2

Rocket R: ΔK = 0.06, 0.05, 0.06, 0.05, 0.05, 0.05, 0.05 and x = 1.80 … 1.16 give eT = 0.035 per BU. If the increments shrink faster than (1 − K), use the power form g(1 − K)q of the paper (Sec. VI-B).

## 3.3 Rates: a straight line through logarithms

Each activity closes a fixed fraction of its remaining gap per BU, so the gap decays exponentially. Within one campaign, regress the logarithm of the gap on cost; minus the slope is the rate:

ln(1 − K) = ln(1 − K0) − rE c        (separate-effects tests)

ln(K̄ − K) = ln(K̄ − K0) − rS c        (simulation, K̄ at the campaign's M)

ln(M̄ − M) = ln(M̄ − M0) − rT c        (integrated tests, M̄ at the campaign's K)

| Campaign | Data | Slope | Rate |
| --- | --- | --- | --- |
| Engine E-1 (E) | c = 0…4; K = .30, .37, .43, .48, .53 | −0.099 | rE = 0.10 |
| CFD (S), K̄ = 0.464 | c = 0…3; K = .20, .27, .32, .36 | −0.309 | rS = 0.30 |
| Ground tests (T), K = 0.50, M̄ = 0.574 | c = 0…3; M = .10, .20, .28, .34 | −0.236 | rT = 0.24 |

## 3.4 Ceilings: regress the plateaus

A plateau is the level at which an activity's marginal rate has fallen below about 10% of its initial value (Table 6, step 5). Regress the simulation plateaus on the demonstrated M of each campaign, and the integrated-test plateaus on the K at which they were run:

K̄(M) = kb + kl M,        M̄(K) = mb + ml K

Org X: simulation plateaus K = 0.47, 0.57, 0.71, 0.82 at M = 0.10, 0.30, 0.50, 0.70 give K̄ = 0.40 + 0.60 M; test plateaus M = 0.36, 0.53, 0.67, 0.84 at K = 0.30, 0.45, 0.60, 0.75 give M̄ = 0.05 + 1.05 K.

Figure S2. Fits of the rates and ceilings for Org X.

## 3.5 The parameter card

| Coefficient | Org X | Paper base | Source |
| --- | --- | --- | --- |
| kb, kl | 0.40, 0.60 | 0.40, 0.60 | CFD plateaus |
| mb, ml | 0.05, 1.05 | 0.05, 1.05 | test plateaus |
| rS; rE; rT | 0.30; 0.10; 0.24 | 0.30; 0.10; 0.22 | campaign rates |
| λT | 1.5 | 0.40 | Rocket R + FAA prior |
| eT | 0.035 | 0.04 | Rocket R increments |
| eE, λE | 0.05, 0.05 | 0.05, 0.05 | prior |
| δK, δM, ρ | 0.06, 0.15, 2 BU | 0.06, 0.15, 2 BU | prior |

# 4. Applying the procedure to a new project

## 4.1 Define the problem (Table 6, step 1)

Project N (fictional): qualify a new upper-stage engine. Claim C1: combustion is stable across the operating envelope. First review: (K, M) = (0.20, 0.10). Target region: K ≥ Kreq = 0.75 and M ≥ Mreq = 0.80. Budget: 30 BU. Exposure limit set by Org X: λT(1 − K)2 ≤ hmax = 0.05 per BU, about a 10% chance of losing a 2-BU integrated test.

## 4.2 The test threshold

An integrated test is worth running only when knowledge supports the target maturity (headroom) and the test hazard is within the exposure limit:

Kneed = (Mreq − mb) / ml,        Khaz = 1 − (hmax/λT)1/2,        Ktest = max(Kneed, Khaz)

Org X: Kneed = (0.80 − 0.05)/1.05 = 0.714; Khaz = 1 − √(0.05/1.5) = 0.817; so Ktest = 0.817 and the exposure limit, not the headroom, decides. In the paper's base case (λT = 0.40), Khaz = 0.65 and headroom decides.

When Khaz > Kneed, step 3b of Table 6 leaves three options: reduce exposure (configuration or envelope), re-approve the limit, or keep building knowledge until K ≥ Ktest. Org X chooses the third. The paper's simulations use the second (the test proceeds once no knowledge deficit remains); Section 4.6 shows how to weigh the two.

| K at the integrated test | Chance of losing a 2-BU test |
| --- | --- |
| 0.20 (today) | 85% |
| 0.50 | 53% |
| 0.714 (Kneed) | 22% |
| 0.817 (Khaz) | 10% |

## 4.3 The decision at each review (Table 6, steps 3–4)

- If M < Mreq and K ≥ Ktest: run the integrated test T (step 3).

- Otherwise (K < Kreq, K < Kneed, or the hazard is above the limit, step 3b): run the activity with the largest net knowledge rate (step 4):

neta = Fa(K, M) − λa(1 − K)2 δK,    with FS = rS[K̄(M) − K]+,  FE = rE(1 − K),  FT = eT(1 − K)

- Screen the chosen activity against cost, schedule and exposure (step 6); if it fails, take the next best.

Worked example: first decision at (0.20, 0.10) K̄(0.10) = 0.40 + 0.60 × 0.10 = 0.46; K = 0.20 < Ktest → step 4. S: 0.30 × (0.46 − 0.20) = 0.0780; hazard 0 → net 0.0780. E: 0.10 × (1 − 0.20) = 0.080; hazard 0.05 × 0.64 = 0.032; loss 0.032 × 0.06 = 0.0019 → net 0.0781. T: 0.035 × 0.80 = 0.028; hazard 1.5 × 0.64 = 0.96; loss 0.0576 → net −0.030. Decision: E (separate-effects tests), practically tied with S. The exact derivative Da of the paper (Eq. (13a)), computed by value iteration, gives +0.98, +0.94 and −2.47 BU saved per BU for S, E and T: the same ranking of T and the same near-tie of S and E.

## 4.4 The review log of Project N (expected path)

| Cost (BU) | K | M | K̄(M) | net S | net E | net T | hazard T | Decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0 | .200 | .100 | .460 | .078 | .078 | −.030 | .96 | E |
| 4 | .465 | .156 | .494 | .009 | .053 | −.007 | .43 | E |
| 8 | .642 | .244 | .546 | .000 | .035 | .001 | .19 | E |
| 12 | .760 | .343 | .606 | .000 | .024 | .003 | .086 | E (3b) |
| 14.8 | .819 | .414 | .648 | — | — | — | .049 | T (step 3) |
| 20.4 | .85 | .80 | — | — | — | — | — | target |

Simulation saturates near 5 BU (K reaches K̄(M)); K passes Kneed near 10 BU, but the hazard is still above the limit, so separate-effects testing continues; at 14.8 BU both conditions hold and integrated testing begins. Without shocks the procedure reaches the target at 20.4 BU; the optimum of the paper's dynamic program needs 20.2 BU.

Figure S3. KMC curve of Project N: procedure (colored) and optimum (grey).

## 4.5 When a shock happens (Table 6, step 5)

Re-assess after every material result. In one simulated realization, a discrepancy during the first hot-fire series at 16.0 BU lowered K from 0.83 to 0.77 and M from 0.54 to 0.39, with 2 BU of rework. K was again below Ktest, so the procedure returned to separate-effects tests until K ≥ 0.817 (20.7 BU) and then completed the integrated tests at 25.9 BU, within budget. The procedure needs no memory: it reads the new state and asks the same two questions.

Figure S4. One realization with a shock, rework and re-plan.

## 4.6 Choosing the exposure limit

| hmax (per BU) | Khaz | Mean cost (BU) | P90 cost (BU) | Shocks per run |
| --- | --- | --- | --- | --- |
| 0.03 | 0.859 | 23.1 | 27.9 | 0.28 |
| 0.05 | 0.817 | 22.3 | 26.4 | 0.39 |
| 0.07 | 0.784 | 22.6 | 28.5 | 0.55 |
| 0.10 | 0.742 | 24.1 | 32.5 | 0.90 |
| optimum (DP) | ≈0.81 | 22.2 | 26.2 | 0.40 |

1000 Monte Carlo runs per row. A limit that is too strict pays for knowledge the test does not need; a loose limit buys shocks and a long tail. For Org X, 0.05 per BU is within 0.4% of the optimum, and the budget of 30 BU is exceeded in about 1 run in 20. Logics that test early (test-first, the naive slope rule) never reach the target with this hazard. The answer depends on the organization: across the 300 parameter sets of the paper (Sec. V-D), waiting for Ktest raised the median excess cost over the optimum from 1.4% to 1.6%, while with the launch-data hazard of Sec. VI-B it lowered it from 1.5% to 0.7%. Run this sweep with your own card before fixing hmax.

# 5. Learning from the project (Table 11, steps 5–6)

After the project, add its records to the log and update the coefficients; the old posterior becomes the new prior. For the test hazard, the integrated testing of Project N accumulated an exposure E = Σ (1 − K)2 Δc = 0.187 over 6.6 BU with one shock. With a Poisson likelihood P(1 | λ) = λE e−λE, the posterior median moves from 1.48 to 1.62 per BU (90%: 0.89–2.89), and the next project's exposure threshold becomes Khaz = 1 − √(0.05/1.62) = 0.824.

Track the coefficients across projects and process changes as organizational indicators: a test hazard above the industry value (0.90) points to more ground and rig testing before flight; a low simulation ceiling with no test data (kb) points to validation-data campaigns; a low knowledge gain per test (eT) points to better instrumentation.

# 6. One-page checklist

- Log cost, activity, K, M and shocks at every review, per claim.

- Fit λT by likelihood on past integrated tests; combine with the public prior.

- Fit the rates with log-linear regressions and the ceilings with regressions on plateaus.

- Keep the paper's base values for coefficients without records.

- Define the claim, target region, budget and exposure limit hmax.

- Compute Kneed, Khaz and Ktest = max(Kneed, Khaz).

- At each review: if M < Mreq and K ≥ Ktest, integrated test; otherwise the activity with the largest net knowledge rate.

- Screen the activity against cost, schedule and exposure.

- Re-assess after every result, shock or saturation; repeat.

- After the project, update the posteriors and track the coefficients.

# 7. Optional checks with the code

The procedure above needs only the spreadsheet. The Python package archived with the paper adds three checks: the optimal policy and the exact derivative Da (solve_dp), a Monte Carlo of the plan (simulate), and a sweep of the exposure limit. Replace the dictionary P in kmc_model.py with the organization's parameter card, set TARGET and X0, and call policy_procedure(K, M, hist, p, tgt, haz_max, wait_haz=True) at each review (wait_haz=False reproduces the paper, where step 3b re-approves the limit). The scripts that reproduce this guide (tutorial/calib.py, apply.py, update.py, figs.py) are included.

Figure S5. The procedure inside the calibration loop (paper, Fig. 8).